## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 1 | 1 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Comprehensive Analysis of Student Interns' Academic and Career Data |  | Project Id: | IP -2815 | Project Manager: | Shivam Rawat |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 1 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2024-06-29 | Project Team Lead: | Shivam Rawat |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 9 |  |  |  |  | 3
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to do required maintenance on time. | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. | Project Manager | High |  | Open | Risk
2 | Risk | Long supply delivery time | Impact on project schedule | Search for vendors who will deliver the resources on timeand within the proposed budget. | Project Manager | Critical |  | Closed | Assumption
3 | Risk | The Dataset contains missing values or errors | Inaccurate analysis | Data cleaning and validation required | Project Manager | Moderate |  | Closed | Issue
4 | Risk | Violating data privacy | Illegal spread of private data | Ensure compliance with relevant data protection laws (e.g., GDPR, HIPAA). | Project Manager | Critical |  | Open | Dependency
5 | Assumption | All available data is correct and complete | Inaccurate data could lead to inaccurate analysis | Thorough data quality check and data validation before data analysis | Project Manager | High |  | Closed
6 | Assumption | Given data is enough for analysis | Inefficient sample data may result in different analysis results | Conduct power analysis to determine the required sample size based on the desired level of significance and effect size. | Project Manager | High |  | Closed | Open
| Issue | Interpreting complex results | Complex results challenge proper interpretation | Involve Domain Experts. | Project Manager | Low |  | Closed
| Issue | The dataset has multiple attributes, increasing complexity | Complex data may lead to longer analysis times and challenges in finding meaningful patterns | Apply dimensionality reduction techniques if necessary | Project Manager | Moderate |  | Open
7 | Dependency | The project relies on data visualization tools to present results | Inability to access these tools would hinder the presentation of insights | Ensure access to preferred data visualization tools | Project Manager | Moderate |  | Closed | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24