## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Shivam Rawat
PROJECT PLAN
PROJECT NAME | Comprehensive Analysis of Student Interns' Academic and Career Data
PROJECT MANAGER | Shivam Rawat
PROJECT DELIVERABLE | Code, Demo Video, Documentation
PROJECT SCOPE
PROJECT START DATE | 16/06/2024
PROJECT END DATE | 30/06/2024
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 16/06/2024 | 16/06/2024 | 1 | COMPLETED
| 1.2 Study Problem |  | 16/06/2024 | 16/06/2024 | 1 | COMPLETED
| 1.3 Create a project charter |  | 16/06/2024 | 16/06/2024 | 1 | COMPLETED
| 1.4 Requirement gathering |  | 16/06/2024 | 16/06/2024 | 1 | COMPLETED
2 Planning
| 2.1 Create SRS |  | 17/06/2024 | 17/06/2024 | 1 | COMPLETED
| 2.2 Create WBS |  | 17/06/2024 | 17/06/2024 | 1 | COMPLETED
| 2.3 Create project plan |  | 18/06/2024 | 19/06/2024 | 2 | COMPLETED
3 Execution
| 3.1 Developing |  | 20/06/2024 | 21/06/2024 | 2 | COMPLETED
| 3.2 Testing |  | 22/06/2024 | 23/06/2024 | 2 | COMPLETED
| 3.3 Deployment |  | 24/06/2024 | 29/06/2024 | 6 | COMPLETED
| 4 Closure |  | 30/06/2024 | 30/06/2024 | 1 | COMPLETED